## Sheet1
No | Assumptions
1 | User-mgmt connectivity is present
2 | connectivity to meo is present
No | Features | Components | Tasks | Effort | Remarks
1 | Login page | applcm-fe | account login | 0.3K | Interaction with user-mgmt
2 | Configuration | applcm-fe | Button to upload config file | 0.2K
|  |  | Delete uploaded config file | 0.2K
3 | LCM operations | applcm-fe | Display all the apps which are currently instantiated | 0.2K | How to get tenant id?
|  |  | Upload app package to be instantiated & instantiate button | 0.3K
|  |  | Terminate button | 0.3K
|  |  | Batch terminate app | 0.3K
|  | applcm-be | API to display all the packages instantiated in tenant & fields similar to appo | 0.3K
|  |  | API for Batch terminate app | 0.5K
4 | App rule management | applcm-fe | Query existing app rules and display | 0.2k
|  |  | Add new dns rule | 0.3K
|  |  | Modify dns rule | 0.3K
|  |  | Delete dns rule | 0.3K
|  |  | Batch delete dns rule | 0.3K
|  |  | Add new traffic rule | 0.3K
|  |  | Modify traffic rule | 0.3K
|  |  | Delete traffic rule | 0.3K
|  |  | Batch delete traffic rule | 0.3K
|  | apprulemgr | support additional fields like tunnel info, dst interface | 0.2k
5 | Monitoring | applcm-fe | Query mep capabilities | 0.5K
|  |  | Query KPI | 0.5K
|  |  | Query CPU/Disk/Memory | 0.5K
|  |  | Monitoring edge node | 0.1k
6 | Synchronization | mecm-fe | Refer inventory api instead of appo for app instance info | 0.1k
|  | appo | Update app instance info to inventory | 0.5K
|  | inventory | create app instance info table | 1k
|  | applcm-be | Update app instance info in inventory whenever new entry added in local db | 2k
7 | Mep portal integration | applcm-fe | details to be discussed | 1k
No | Components | Effort
1 | Meo-fe | 0.1k
2 | Meo-be | 1k
3 | Mepm-fe | 4k
4 | mepm-be | 2k