## edgeT
Task | Duedate | status
Arch review | 2020-10-28 | done
New Repo creation - TSC review | 2020-11-04 | in-progress
New repo creation - gitee request | 2020-11-04
seed code preparation | 2020-11-10
seed code testing | 2020-11-16
jenkins job (docker, pr) | 2020-11-16
portal support | 2020-11-24
CLI support | 2020-11-30
add eg test cases for user-mgmt, appstore, dev, mecm and mep | 2020-12-08
user-mgmt integration (streach goal) | 2020-12-08
portal workflow support (streach goal) | 2020-12-08