## vtp
Task | Effort (man-days)
Setup project in gitee | 1
Review with TSC for new project repo 'edgeT' | 1
seed code vtp (controller and engine + plugins) | 3
enable jenkins jobs (pr, docker) | 1
portal support (new feature) | 15
scenario, sut and result management for edge gallery support (updated feature) | 10
REST API review (portal workflow design) | 3
add eg test cases for user-mgmt, appstore, dev, mecm and mep (low priority) | 10
integrate test case support addition | 5
total | 49