## Sheet1
Type | Activity | Owner | Expected Completion | Status | Remark
Analysis | Initial Framework & API Analysis | Gaurav | 2020-08-07 | Completed
| DB Analysis for Cloud Components | Vidya | 2020-08-14 | Completed | Based on analysis POSTGRES is selected
| Workflow Engine Analysis | Shashi | 2020-08-14 | Completed | Based on analysis Camunda is selected
| IDE/POM plugin/settings for JAVA | Khemendra | 2020-08-14 | Completed
| IDE/POM plugin/settings for GOLANG | Khemendra/Vidya | 2020-08-14 | Completed
| Error handling analysis for Springboot | Vidya | 2020-08-14 | Completed
| Certificate/Password to MECM module | Gaurav/Chuanyu | 2020-08-14 | Completed
| GRPC vs REST for internal communication | Vidya | 2020-08-17 | Completed
| APM to handle repo in generic way | Vidya | 2020-08-21 | Completed
Development | Inital Framework Commit | Gaurav/Shashi | 2020-08-07 | Completed
| Initial API Commit | Gaurav/Shashi | 2020-08-07 | Completed
| Docker build related artifact commit | Gaurav | 2020-08-14 | Completed
| Swagger related artifact commit | Vidya | 2020-08-14 | Completed
| Enable Coding style/Security plugin for MECM module | Gaurav/Khemendra | 2020-08-14 | Completed
| Second level of API commit (monitoring, plugin) | Shashi/Rama | 2020-08-17 | Completed
| Model commits | Shashi/Rama/Vidya | 2020-08-17 | Completed
| APPO Implementation | Shashi | 2020-08-28 | In-Progress
| APM Implementation | Vidya | 2020-08-28 | In-Progress
| APPLCM Implementation | Rama | 2020-08-28 | In-Progress
| ESR Implementation | Gaurav | 2020-08-28 | In-Progress
Integration | Integration (among MECM components, MECM-FE (Extended Goal)) test | All | 2020-08-31 | Open
| Clean code/Static check tools fixes | All | 2020-08-31 | Open
Test Coverage (40%) | Unit Test cases | All | 2020-08-04 | Open
Secure Design Compliance | Secure design analysis and Implementation | All | 2020-08-04 | Open